Event Management guidance

- Get approval on initial idea from the Core Group

- Fill in the event organising form (lead person or the relevant group)

- Distribute the plan to the relevant people

- Elect an organiser to keep checking up on progress of the other members

- Follow the project plan

- Arrange regular project meetings if this is required

- Event

- Debrief on the event

Notes:

For Park based events, there is an application form that must be filled out and for some events (unlikely to affect Transition but would depend on the event) a £75 deposit must be put down.

Worcester City Council (through Ruth) can print leaflets, posters etc in reasonable quantities. Please remember to allow a couple of days for printing and be prepared to pick them up / supply address for posting.

When sending materials through for printing, please state:

- Quantities

- Size

- Colour or black and white

- Whether required quicker than the standard 2-day turnaround

- Address for posting or if they will be collected, by whom and when

Arranging events in conjunction with other things can be a good way of ensuring a certain number of people attend. For example, booking the Guildhall with another event in the other half of the hall for the Energy Fayre worked really well.

| Organiser/s and roles | Minimum roles: Leader - Publicity (press release and leaflets/posters) - Publicity (website and social media) - Tracking progress - Transportation - |
| --- | --- |
| Title |  |
| Description/idea |  |
| Suggested date or dates |  |
| Time/s |  |
| Venue |  |
| Breakdown of probable costs |  |
| Staffing needs |  |
| Prior booking arrangements (as it will go on website) |  |
| Contact details (as it will go on website) | eg. transitionworcester@gmail.com |
| Contact details (for internal use – recognising these may be different to above) |  |
| Any further details (eg equipment, printed materials etc) |  |

Project Plan

Task List – customise as necessary for the event, these are ideas:

| 4 weeks before the event | Design leaflet and poster and send to Council with amounts required of both Printing of leaflets / posters (Ruth) Discussion re press release – check with Ruth that the council are happy to send out to contacts Other funding needs? Talk to Justin and Ruth – before expenditure. Money is unlikely to be refunded if expenditure is not approved first. |
| --- | --- |
| 3 weeks before the event | Any external people required have been invited and know what is expected of them Posters to be distributed (see Publicity doc for a list of suggested places) – likely to need a car to do this Advertise the event on website, Facebook and Twitter |
| 2 weeks before the event | Send press release to Council and be prepared for changes to be made and a final check through being required Ensure that press release is sent out. Check that TW stand materials are accessible and whether more TW leaflets need printing |
| 1 week before the event | Phone media contacts to check uptake of the press release Arrange for pick up of the TW stand materials, making sure that there are leaflets, mailing list sign up sheets and the TW donations bucket. |
| 2 days before the event | Re-post on Facebook/Twitter/website reminding people and asking them to attend / publicise / bring friends Check with any external people that they have the information they need and mobile phone numbers for on-the-day contact. |
| On the day | Ensure that people are encouraged to sign up for TW updates and sign the Facebook group etc. Ensure that people are encouraged to give donations towards TW. |